Management Requirements for

“Space for UK on COVID-19 and other pandemics”

Appendix 3 to Contract

TABLE OF CONTENTS

[1 INTRODUCTION 2](#_Toc37078996)

[2 MILESTONE REVIEW MEETINGS (MRM) AND ASSOCIATED DELIVERABLE DOCUMENTS 2](#_Toc37078997)

[3 MRM 3](#_Toc37078998)

[3.1 Negotiation Meeting (NM) 4](#_Toc37078999)

[3.2 Baseline Design Review (BDR) 4](#_Toc37079000)

[3.3 Acceptance Test (AT) 4](#_Toc37079001)

[3.4 Final Review (FR) 4](#_Toc37079002)

[4 ADDITIONAL REQUIREMENTS 5](#_Toc37079003)

[4.1 Document Confidentiality 5](#_Toc37079004)

[4.2 Contractor Project Manager 5](#_Toc37079005)

[4.3 Reporting – Minutes of Meetings (MOM) 5](#_Toc37079006)

[4.4 Electronic Documentation 6](#_Toc37079007)

[4.5 List of Deliverables 7](#_Toc37079008)

[ANNEX A. List of ACronyms 14](#_Toc37079009)

# INTRODUCTION

The “Management Requirements” (MR) document provides a set of guidelines to the Contractor in charge of the Demonstration Project for the management of the project during its life-cycle, i.e. from the Negotiation Meeting, which precedes the signature of the Contract, until the Final Review.

# MILESTONE REVIEW MEETINGS (MRM) AND ASSOCIATED DELIVERABLE DOCUMENTS

The following paragraphs describe the sequence of Milestone Review Meetings (MRM) that will mark the implementation of the project. Through the sequence of MRM, ESA will monitor the progress of the contractual activities, assess the quality and completeness of the deliverables and, when relevant, will authorise the relevant milestone payments.

For each of the review meetings indicated below, the MR do also provide guidelines on:

* Their main purpose
* The applicable deliverables

Each of the MRM shall be attended by at least by the Project Manager.

The documentation supporting each milestone review meeting shall be delivered to ESA no later than five (5) working days before the meeting takes place.

Besides the review meetings indicated below, additional technical meetings can be envisaged if required by the specific implementation approach proposed by the Contractor (e.g. in case of an AGILE approach this is quite often required).

The following documents shall be delivered at the different MRMs, as specified in section 4. of this document:

1. **Requirements Document (RD)**   
   The purpose of the Requirements Document is to make sure that all the user’s needs are listed and agreed. These needs are turned into measurable requirements which can be later tested by the Contractor in the System Verification Document
2. **System and Service Architecture (SSA)**   
   The purpose of the System and Service Architecture document is to specify the overall pilot system starting from the high level architecture down to its constituent building blocks. The SSA shall describe the extent of development and/or integration of hardware, software and content elements and choice of the most appropriate system to be used in the project.
3. **System Verification Document (SVD)**   
   The purpose of the System Verification Document is to plan the repeatable tests which will show how the system meets the requirements set out in the Requirements Document. Once the tests have been planned they will be run by the Contractor and the results recorded and presented to ESA
4. **Pilot Utilisation (PilUP)**   
   The Pilot Utilisation Plan is a practical guide to how the pilot shall be run. It demonstrates that the Contractor has thought about the practical consequences of taking the product and services to the field. The Pilot stage of the project is one of the most hectic parts of the project and it’s easy to lose track of the objectives when trying to solve urgent issues. That’s where the KPIs come in. They help keeping the team focussed on what things are important, like getting great customer feedback scores and making sure that the product/service is used as much as possible during the Pilot
5. **Project Web Page (PWP)**   
   The Project Web Page is intended for publication on the ESA Business Applications portal and shall not contain any proprietary information. Whwnever relevant, the Contractor shall provide an updated version of the “Current Status” paragraph of the Project Web Page.
6. **Final Report (FREP)**   
   The Final Report shall present in about 20-30 pages (pictures, Index and Appendix included) an overview of the activities carried out during the project. It is “the business visiting card” of the project presenting in a concise way the business idea and the service developed by the project, the main activities carried out during the project, highlighting the pilot results and the intended commercial roll-out strategy, the achievements and lessons learnt, any other relevant/important topics and it shall include a brochure of the product/service. The Final Report is intended for general audience and publication. Therefore, it shall not contain any sensitive information, nor complex technical details. It should provide some highly interesting or impactful pictures (e.g. users while they utilise the system during the pilot stage) and graphs, diagrams or tables as needed

The templates to be used for the deliverable documents of the different MRMs, as well as the draft Agendas for the MRM, can be found at this URL:

[**https://business.esa.int/documents**](https://business.esa.int/documents)

# MRM

The following MRM typically apply to a Demonstration Project that follows a waterfall development approach. The Contractor can follow an alternative approach, providing it is properly described in the Full Proposal and agreed by ESA..

## Negotiation Meeting (NM)

The purpose of the Negotiation Meeting (NM) is to confirm that all points of clarification and negotiation raised by ESA have been successfully addressed, to discuss and agree on the project planning via the Project Bar Chart (PBC), to negotiate the contract and to review the activities for the next MRM.

The NM is also the opportunity for the team to meet the ESA Technical Officer and create the basis for an effective working cooperation during the rest of the project.

## Baseline Design Review (BDR)

Between the NM and the Baseline Design Review (BDR) the Contractor shall finalise the User Needs and the User Requirements in cooperation with the pilot users, and identify a mature set of System Requirements. Needs and Requirements will be described in the Requirement Document (RD).

The RD is the key deliverable of the BDR milestone.

Additional deliverables of the BDR are:

* The **Project Web Page (PWP)**

In preparation of the BDR, the Contractor may organise a **User Workshop** inviting the pilot Users and Customers, with the objective to consolidate and validate the RD.

## Acceptance Test (AT)

At the end of the development and integration activities and prior to starting the deployment of the pilot-demonstration system, the Contractor shall set up an Acceptance Test (AT) MRM devoted to demonstrate that the system/service is compliant with the set of requirements agreed at the BDR.

The SVD is the key deliverable of the AT milestone.

During the AT, a subset of the tests agreed with ESA will be repeated in-front-of the ESA Technical Officer and the results will be attached to the minutes of the AT meeting.

Whenever practical, the verification session with ESA can take place via a web conference (e.g. WebEx) during which the contractor shall follow a test plan which involves navigating the user interface. This part of the verification session shall be documented via a video/screengrab to be added to the minutes of the milestone meeting.

The successful completion of the AT will kick-off the activities for the deployment of the pilot-demonstration system.

## Final Review (FR)

At the Final Review (FR) the Contractor shall present a global overview of the activities carried out during the project and summarise (within the PilUP document) the outcome of the pilot stage, including conclusions and recommendations gathered from the Contractor and the pilot users. At the FR the Contractor shall also present the action plan associated with the service operational/commercial deployment, as applicable.

The key deliverables of the FR Review Milestone are:

* **The Final Report (FREP)**, in which the Contractor, in about 25 pages, shall present a summary of the activities carried out in the frame of the project. This document shall not contain commercially sensitive information
* **Summary and Achievements (S&A)** shall provide a concise overview of the project and its main achievements. This document will be used internally by ESA, and whenever needed for reporting to the National Delegations of the ESA Member States
* **The Final Data Package (FDP)**, consisting in an archive containing the latest version of all deliverables (BP, RD, PWP, SSA, SVD, PilUP, FREP, PBC, S&A), and the collection of Digital Media (DM) consisting of digital video, brochure and pictures aimed for the branding and marketing of the product(s) and service(s) developed

As part of the FR, a bilateral discussion between the project team and ESA about what worked and what not in the context of the project shall be carried out. The main points shall be recorded as part of the Minuet of the Meeting of the FR.

# ADDITIONAL REQUIREMENTS

## Document Confidentiality

All deliverable documents produced in the frame of the project and marked as “Proprietary Information” will be treated in confidence (see Clause 52.2 of the ESA General Clauses and Conditions). Project Web Page and the Final Report shall not contain any “Proprietary Information”, since they are intended for public dissemination.

## Contractor Project Manager

The nominated Project Manager (PM) shall be responsible for the management and execution of all work to be performed and for the coordination and control of the work within the project team. The PM will be the official point of contact with the Agency during the execution of the work.

During the contract execution, the PM shall notify the Agency of any critical risk that may arise, analysing the cause, assessing the potential impacts on the project in terms of time, objectives and scope and formulating in the shortest possible time a mitigation strategy.

## Reporting – Minutes of Meetings (MOM)

Written Minutes of Meetings attended by ESA shall be prepared and made available by the Contractor, and have to be signed at the end of the meeting. The minutes shall clearly identify all agreements made and actions accepted together with, where relevant, an update of the Action Item List.

To establish a uniform and consistent procedure to identify the Action Items among the different ARTES projects, the Contractor shall keep track of the Action Items adopting the following action identification scheme:

##### Action X.Y

where *X* is the identifier of the meeting (0: Negotiation Meeting, 1: First MRM, 2: Second MRM, etc.), and *Y* is the Action number starting from 01 at each new meeting.

.

In case of urgent or critical problems, new Actions can be originated by the Agency and/or by the Contractor even outside the normal scheduled meetings.

## Electronic Documentation

All documentation shall be delivered in electronic form, using preferably MS Word or Adobe Acrobatformat with all pictures and tables embedded in the document. The documentation shall not impose limitations on the ability to be commented and printed.

## List of Deliverables

The items that will be delivered during the project are summarised in the table below.

Table 1 List of deliverables

| Name | Deliverable | Initial Submission | Final Submission |
| --- | --- | --- | --- |
| MOM | Minutes of Meetings | NM | FR |
| RD | Requirements Document | with the proposal | FR |
| SSA | System and Service Architecture | with the proposal | FR |
| PilUP | Pilot-Demonstration Utilisation Plan | with the proposal | FR |
| SVD | System Verification Document | AT | AT |
| PWP | Project Web Page | BDR | FR |
| FREP | Final Report | FR |  |
| FDP | Final Data Package | FR |  |

Each deliverable document shall include a title page reporting the project name, the contract number, the title of the document, a reference identifier, the author(s) and related organisation(s), the date of issue and the revision number.

Layout of Contract Closure Documentation

ESA/ESTEC Contract No. ...... [INSERT NUMBER]

“[INSERT ACTIVITY TITLE]”,

hereinafter referred as the “Contract”

Section 1 – Parties, Contract Duration and Financial Information

|  |  |  |  |
| --- | --- | --- | --- |
| Contractor | | [CONTRACTOR NAME] | |
| Sub-Contractor(s)  (state if not applicable) | | [NAME AND COUNTRY] | |
| Contract Duration | | From:  To: | Phase 1 from:  to: |
| Phase n from:  to: |
| Total Contract Price  (including all CCNs, Work Orders, Call of Orders)  and Total Contract Value  (in case of co-funding; state if not applicable) | | | EUR  EUR |
| Broken down as follows: | Original Contract Price  and original Contract Value  (in case of co-funding; state if not applicable) | | XXX EUR (XXX EUR)  EUR |
| CCN x to n | | **EUR** in total |

Section 2 – Recapitulation of Deliverable Items

2.1 Items deliverable under the Contract

If any of the columns do not apply to the item in questions, please indicate “n/a”.

Table 2.1.1 – Items deliverable according to the Statement of Work

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Type | Name /  Title | Description | Location[[1]](#footnote-2) | Property of | Rights granted / Specific IPR Conditions[[2]](#footnote-3) |
| Documentation |  | According to the MR list | n/a | n/a |  |
| Hardware |  |  |  |  |  |
| Software |  | Delivery at contractor point |  |  |  |
| Other |  |  |  |  |  |

No Fixed Asset has been acquired under the Contract by the Contractor and/or its Sub-Contractor(s).

Table 2.1.2 – Background Information used and delivered under the Contract (see Clause 57 of the General Clauses and Conditions)

The following background information has been incorporated in the deliverable(s):

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Proprietary Information  (title, description) | Owner  (Contractor, Sub-Contractor(s), Third Party/ies) | Affected deliverable  (which documents, hardware, software, etc.) | Description impact on ESA’s rights to the deliverable[[3]](#footnote-4) | Other/comments |
|  |  |  |  |  |

Section 4 – Statement of Invention

**[OPTION 1**: NO INVENTION]

In accordance with the provisions of the above Contract, ……………[Company] hereby certifies both on its own behalf and that of its Contractor/Subcontractor(s), that no Intellectual Property Right(s) has(ve) been registered in the course of or resulting from work undertaken for the purpose of this Contract; and that no inventions have been made in the course of or resulting from work undertaken for the purpose of this Contract that generated knowledge that could be registered as Intellectual Property Rights.

[**OPTION 2:** INVENTION]

In accordance with the provisions of the above Contract, ……………[Company] hereby certifies both on its own behalf and that of its Contractor/Subcontractor(s) that the following Intellectual Property Right(s) has(ve) been registered in the course of or resulting from work undertaken for the purpose of this Contract.

…………………….

[**OPTION**]: In accordance with the provisions of the above Contract, ……………[Company] hereby certifies both on its own behalf and that of its Contractor/Subcontractor(s) that the following inventions have been made in the course of or resulting from work undertaken for the purpose of this Contract but have not been registered as Intellectual Property Rights:

…………………….

[**OPTION**]: In accordance with the provisions of the above Contract, ……………[Company] hereby certifies both on its own behalf and that of its Contractor/Subcontractor(s) that the following inventions have been made in the course of or resulting from work undertaken for the purpose of this Contract and are foreseen for and/or in the process of registration:

The Agency’s rights on such registered and/or unregistered Intellectual Property Rights shall be in accordance with the ESA GCC Part II provisions as amended by the above Contract.

|  |  |
| --- | --- |
| The above statements provided in the various sections of this Annex A “Layout for Contract Closure Documentation” for ESA Contract No. **4000xxxxxx/xx/XX/XXX/xxx *[insert the corresponding Contract number*]** have been made after due verifications.  The Contractor furthermore certifies that all its obligations with regard to Fixed Assets, if any, have been fulfilled.  If required by ESA, an updated version shall be provided for incorporating amendments requested by ESA. | |
| Name of Contractor:  *[insert Contractor name]* | |
| Authorised signatory:  *[insert Authorised signatory full name]* | *[signature of the Authorised signatory*] |
| Date:  [insert date] | |

1. List of ACronyms

|  |  |
| --- | --- |
| ARTES | Advanced Research in Telecommunication Systems |
| AT | Acceptance Tests |
| BDR | Baseline Design Review |
| ESA | European Space Agency |
| FDP | Final Data Package |
| FR | Final Review |
| FREP | Final Report |
| HW | Hardware |
| KPI | Key Performance Indicator |
| MOM | Minutes of Meetings |
| MR | Management Requirements |
| MRM | Milestone Review Meeting |
| NM | Negotiation Meeting |
| PBC | Project Bar Chart |
| PilUP | Pilot-Demonstration Utilisation Plan |
| PM | Project Manager |
| PWP | Project Web Page |
| RD | Requirements Document |
| S&A | Summary and Achievements |
| SSA | System and Service Architecture |
| SVD | System Verification Document |
| SW | Software |

1. In case the item is not delivered to ESA, please indicate the location of the deliverable and the reason for non-delivery (e.g. loan agreement, waiver, future delivery, etc.) [↑](#footnote-ref-2)
2. e.g. IPR constraints, deliverable containing proprietary background information (see also 2.1.4 below) [↑](#footnote-ref-3)
3. if not explicitly stated otherwise, the contractual stipulations shall prevail in case of conflict with the description provided in this table [↑](#footnote-ref-4)